## Slide 1: Intro to Software Engineering
LECTURE : SOFTWARE PROJECT MANAGEMENT

## Slide 2: Software Project Management
Software & Project Management
  Corporate America spends more than $275 billion each year on approximately 200,000 application software development projects
  Most of these projects will fail for lack of skilled project management
Management problems were more frequently dominant cause than technical problems
Schedule overruns were more common (89%) than cost overruns (62%)
KPGM’s Survey in UK

## Slide 3: Software Project Management (2)
Success Factors
  User involvement – 20 points
  Executive Support – 15 points
  Clear Business Objectives – 15 points
  Experienced Project Manager – 15 points
  Small milestones – 10 points
  Firm basic requirements – 5 points
  Competent staff – 5 points
  Proper planning – 5 points
  Ownership – 5 points
  Others – 5 points
  Most of these points are of Management concern

## Slide 4: Software Project Management (3)
Primary causes of software runaway
  Project Objectives not fully specified
  Bad planning and estimating
  Technology new to the organization
  Inadequate/No project management methodology
  Insufficient senior staff on the team
  Poor performance by Supplier of hardware/software

## Slide 5: In a nutshell
“Organizations that attempt to put software engineering discipline in place before putting project management discipline in place are domed to fail”

## Slide 6: Project
“A temporary endeavor undertaken to create a unique product, service or result”
A project is a temporary endeavor undertaken to create a unique product or service
Project Management Institute

## Slide 7: Project Management
Project management is
The art of managing projects to a successful completion.
The Project Management Triple Constraint:
Scope
Time
Cost
Quality

## Slide 9: Terminology : Deliverable
Work product that is provided to the client
      mock-up,
      demonstration,
      prototype,
      report,
      presentation,
      Documentation
      code
      Release of a system or subsystem to customers or users.
Notes: A schedule along with time estimates.
A prioritized list of features.
An example of the main page so we can review look and feel.
An archive of the old website
The final website

## Slide 10: Terminology : Milestone
  Completion of a specified set of activities (e.g., delivery of a deliverable, completion of a process step)
  A milestone is a checkpoint in the project
    A milestone has
      A description of the point
      A date
      A person or persons who are responsible
  A milestone may or may not have a deliverable associated with it.
    A deliverable has
      A description of a deliverable (scope)
      A date (time)
      A person or persons who are responsible (cost)

## Slide 11: Terminology : Work Package
A work package is a large, logically distinct section of work:
– typically at least 12 months duration;
– may include multiple concurrent activities;
– independent of other activities
– but may depend on, or feed into other activities; – typically allocated to a single team.

## Slide 12: Terminology : Work Product
A work product is a report, diagram, or collection of documents used by the business analyst during the requirements development process.
A work product may or may not become a deliverable.
It can be used to share information with stakeholders, elicit requirements, provide status
work product includes the beginning stages of a project, proposals, agendas, reports, analysis and information on the project. A deliverable, on the other hand, is the end result of the project.

## Slide 13: Terminology : Task
A task is typically a much smaller piece of work:
– A part of a workpackage.
– typically 3–6 person months effort;
– may be dependent on other concurrent activities;
– typically allocated to a single person.

## Slide 14: Terminology : Activity
– Must have a clear start and a clear stop
– Must have a duration that can be forecasted
– May require the completion of other activities before it begins
– Should have some deliverables for ease of monitoring

## Slide 15: Terminology
Event
The end of a group of activities, e.g., agreement by all parties on the budget and plan
Dependency
An activity that cannot begin until some event is reached
Resource
Staff, time, equipment, or other limited resources required by an activity.

## Slide 16: Standard Approach to Project Management
The scope of the project is defined early in the process.
The development is divided into tasks and milestones.
Estimates are made of the time and resources needed for each task.
The estimates are combined to create a schedule and a plan.
Progress is continually reviewed against the plan, perhaps weekly.
The plan is modified by changes to scope, time, resources, etc.
Typically the plan is managed by a separate project management team, not by the software developers.

## Slide 17: Product and the Project Life Cycles
Notes: Projects are finite; they have a defined start and end date and are essentially one and done.
A product focused model, on the other hand, is tied to the natural product lifecycle—you are never done until the product reaches its end of life. Resources are also flexible to meet the demands of the product lifecycle and your backlog of items has a much smaller time horizon. The product-oriented approach makes it much easier to manage the ongoing health and maintenance of the product.
A big project, however, can last years. Alternatively, a typical product backlog in a product model, usually has a horizon of no more than a few months.
PMBOK 2004: Add more
Divestment>> remove, take off, remove
In some application areas, such as new product development or software development, organizations consider the
project life cycle as part of the product life cycle.

## Slide 18: Phases in a Project Life Cycle

## Slide 19: Project Charter Example: Web Site
One page!

## Slide 20: Project Management Life Cycle
Processes/Activities of the 5 phases (Process Groups 2004) are as:
1. Scope the Project
State the Problem/ Opportunity
Establish the project goal
Define project Objectives
Identify the success criteria
List assumptions, risks, obstacles
3. Launch the Plan
Recruit and organize project team
Establish team operating rules
Level resources
Schedule work packages
Document work packages
5. Close Out
Obtain client acceptance
Install project deliverables
Complete project documentation
Complete post-implementation audit
Issue final project report
4. Monitor/ Control Progress
Establish progress reporting system
Install change control tools/process
Define problem-escalation process
Monitor project progress vs plan
Revise Plan
2. Develop detail Plan
Identify project activities
Estimate activity duration
Determine resource requirements
Construct / analyze project network
Prepare project proposal
Notes: Commonalities between phases for Product and Project (system) development with project phases 1 00,101

## Slide 21: Knowledge Areas for Project Management
Project Integration Management
Project Scope management
Project Time Management
Project Cost Management
Project Quality Management
Project Human Resource Management
Project Communications Management
Project Risk Management
Project Procurement Management
[PMBOK PMI]
Notes: +PMI-8
The knowledge areas are the core technical subject matter, which are necessary for effective project management.

## Slide 22
1. Project Planning

## Slide 23: Project Planning Tools
Critical Path Method, Gantt charts, Activity bar charts
• Build a work-plan from activity data.
• Display work-plan in graphical or tabular form.
Project planning software (e.g., Microsoft Project)
• Maintain a database of activities and related data
• Calculate and display schedules
• Manage progress reports

## Slide 24: 1. Software Project Planning
The purpose of the Project Plan is to
  define and establish the management strategy for achieving the goals of the project.
The project development plan is used to:
    Guide project execution.
    Document project planning assumptions.
    Document project planning decisions regarding alternatives chosen.
    Facilitate communication among stakeholders.
    Define key management reviews (as to content, extent, and timing).
    Provide a baseline for progress measurement and project control.
Notes: Extent >> amount

## Slide 26: Planning Process Flow

## Slide 27: Types of Plans
Software development plan :The central plan, which describes how the system will be developed.
Quality assurance plan : Specifies the quality procedures & standards to be used.
Validation plan. Defines how a client will validate the system that has been developed.

## Slide 28: Types of Plans
Configuration management plan : Defines how the system will be configured and installed.
Maintenance plan : Defines how the system will be maintained.
Staff development plan: Describes how the skills of the participants will be developed.

## Slide 29: The Project Plan- Format
Contents
Many format; common sections are: (kathy -62)
Introduction or Overview
  Project Name, Description and Need it addresses, Sponsor's name, Name of PM, Deliverables (Brief), Reference Material, List of definitions.
Project Organization
  Org. chart, Responsibilities, Other Org. or process related info.
Management and Technical Approach
  Manage Objectives, project control, Risk Manage, Staffing, Technical Processes.
Project Scope
  Major Work Packages/WBS, Key Deliverables, Other Work related Info.,
Project Schedule
  Summary/Detail Schedules
Budget
  Summary/Detail budget,

## Slide 30
2. Scope Definition

## Slide 31: The first step - define the Scope
Scope
& Quality
Cost
Time
Resource Availability
“Scope” The term may refer to:
  Product scope - the features and functions that are to be included in a product or service.
  Project scope - the work that must be done in order to deliver a product (with the specified features and functions).
Product Scope is defined in the product requirements and is the subject of the product life cycle
Project Scope is defined in the project charter and is the subject of the project plan (Kathy-ch4)

## Slide 32: Decomposition
Identify the major elements (deliverable) of the project.
Identify constituent elements (Work Products) of the deliverable.
Decide if adequate cost and duration estimates can be developed at this level of detail for each element.
Subdividing the major project deliverables into smaller, more manageable
Components (products) in sufficient detail
          to support future project activities (planning, executing, controlling, and closing)
        Requires Steps:

## Slide 33: WBS-Work Breakdown Structure
Overall work has to be decomposed into manageable units
Complex tasks are broken down into subtasks and further refined called Work Breakdown Structures (WBS)
Notes: Improve accuracy of cost, time, and resource estimates.
Define a baseline for performance measurement and control.
Facilitate clear responsibility assignments.

## Slide 34: WBS-Work Breakdown Structure
There are many ways of breaking down the activities in a project, but the most usual is into:
    – work packages;
    – tasks/Activities
    – deliverables/Work Products
    – milestones

## Slide 35: WBS Framework
A framework dictating the number of levels and the nature of each level may be imposed on a WBS (e.g. IBM recommended five levels):
  Level 1: Project.
  Level 2: Deliverables (such as software, manuals and training courses)
  Level 3: Components; Which are the key work items needed to produce deliverables (e.g. modules and tests required to produce the system software)
  Level 4: Activities (Work-packages which are major work items, or collections of related tasks, required to produce a component)
  Level 5: Tasks (tasks that will normally be the responsibility of a single person).

## Slide 36: Hierarchy of WBS

## Slide 37: WBS Template for Software Development Project

## Slide 38: Example

## Slide 39: Examples

## Slide 40: 3. Activity Planning

## Slide 41: Planning And Scheduling
Need to develop a schedule in which planned start and end dates are assigned to all activities
        Activity precedence & Dependencies
        Activity duration
        Available resources
Steps
Define activities (Gantt chart )
Sequence activities (CPM )
Estimate time (PERT)

## Slide 42: Task Dependencies
Task Dependencies (relationships)
Finish-to-start (FS): Task (B) cannot start until task (A) finishes
A
B
Start-to-start (SS): Task (B) cannot start until task (A) starts
A
B
Finish-to-Finish (FF): Task (B) cannot finish until task (A) finishes
A
B
Start-to-finish (SF): Task (B) cannot finish until task (A) starts
A
B
Notes: Kathy

## Slide 43: Scheduling as precedence
A: Designing
B: Coding
F
S
A: Testing
B: Debugging
S
S
A: Coding
B: Unit Testing
F
F
A: Release
B: Bug Fixing
S
F

## Slide 44: Gantt chart - Define activities
Developed in 1918 by H.L. Gantt
■ Graph or bar chart with a bar for each project activity that shows passage of time ■ Provides visual display of project schedule

## Slide 45: Gantt Chart

## Slide 46: Gantt Chart

## Slide 47: Project Network Diagrams
Project network diagrams (PND) are the preferred technique for showing activity sequencing
A project network diagram is a schematic display of the logical relationships among, or sequencing of, project activities
Arrow Diagramming Method (ADM)
  Also called activity-on-arrow (AOA) project network diagrams
  Activities are represented by arrows
  Nodes or circles are the starting and ending points of activities
  Can only show finish-to-start dependencies
Precedence Diagramming Method (PDM)
  Activities are represented by boxes
  Arrows show relationships between activities
  More popular than ADM method and used by project management software
  Better at showing different types of dependencies
Notes: Network (precedence) diagram – diagram of project activities that shows sequential relationships by the use of arrows and nodes.
Activity-on-arrow (AOA) – a network diagram convention in which arrows designate activities.
Activity-on-node (AON) – a network diagram convention in which nodes designate activities.

## Slide 48: Basic Project Network Diagrams (PND)…..
1
3
2
B=?
A=?
4
C=?
5
D
6
F
8
J
7
G
E
H
I
AOA (ADM);
CPM adds more inf at nodes
Task Box of MS Project 2000: Activity Name Start: ID: Finish: Dur: Resource:
B
Start: ID:
Finish: Dur:
Res:
C
Start: ID:
Finish: Dur:
Res:
G
Start: ID:
Finish: Dur:
Res:
F
Start: ID:
Finish: Dur:
Res:
E
Start: ID:
Finish: Dur:
Res:
D
Start: ID:
Finish: Dur:
Res:
H
Start: ID:
Finish: Dur:
Res:
J
Start: ID:
Finish: Dur:
Res:
I
Start: ID:
Finish: Dur:
Res:
A
Start: ID:
Finish: Dur:
Res:
PDM

## Slide 49: Terminology: Network Diagram
Path
  Sequence of activities that leads from the starting node to the finishing node
Critical path
  The longest path; determines expected project duration
Critical activities
  Activities on the critical path
Slack
  Allowable slippage for path; the difference the length of path and the length of critical path

## Slide 50: Terminology: Network Diagram
Slack time (also known as float)
  is the amount of delay expressed in units of time that could be tolerated in the starting time or completion time of an activity without causing a delay in the completion of the project.
Slack time is the difference between the late finish and the early finish (LF-EF).
If the result is greater than zero, then the activity has a range of time in which it can start and finish without delaying the project completion date
Notes: If an activity has zero slack, it determines the project completion date. In other words, all the activities on the critical path must be done on their earliest schedule or the project completion date will suffer.
If an activity with total slack greater than zero were to be delayed beyond its late finish date, it would become a critical path activity and cause the completion date to be delayed.
The sequence of activities that has zero slack is defined as the critical path
In general, the critical path is the path that has minimum slack.

## Slide 51: Sequence activities (Critical Path Method CPM )
project network analysis technique used to predict total project Duration
primary objectives:
Planning the project to complete it as quickly as possible
Identifying those activities where a delay in their execution
  affect the overall end date of the project or ‘later activities’ start dates.
represents activities as links (arrowed lines) in the graph
nodes (circles) represent the events of activities start and finish.
A link represents an activity (and has duration)
A slack period is one in which there is not much work or activity.
  Slack time = Latest start time - Earliest start time.

## Slide 52: Critical path method
A forward pass analysis performs schedule calculations that identify the early start and ﬁnish dates of activities and the project
A backward pass analysis performs schedule calculations that identify the late start and ﬁnish dates of activities and the project, as well as total and free ﬂoat
Total ﬂoat (TF) is the amount of time an activity can be delayed without delaying the project as a whole
Free ﬂoat (FF) is the amount of time an activity can be delayed without delaying its successor (dependent) activities
Note that total ﬂoat is global to the project, while free ﬂoat is local to the neighborhood of the activity

## Slide 53: Terminology: CPM
Network activities
  ES: early start
  EF: early finish
  LS: late start
  LF: late finish
Used to determine
  Expected project duration
  Slack time
  Critical path

## Slide 54: CPM –Forward Pass
ES : 1
EF : ES +Duration - 1
ES of Next Activity : EF of previous activity +1
EF of next Activity : ES+Duration-1

## Slide 55: CPM – Backsword Pass
LF = EF of last activity
LS = LF-Duration+1
LF of prev Activity = LS -1 of Prev Activity
https://www.pmexamsmartnotes.com/how-to-calculate-critical-path-float-and-early-and-late-starts-and-finishes/3/
Notes: https://www.pmexamsmartnotes.com/how-to-calculate-critical-path-float-and-early-and-late-starts-and-finishes/3/

## Slide 56: Example

## Slide 61
Activity |  | Duration (weeks) | Precedents
A | Hardware selection | 6 | 
B | Software design | 4 | 
C | Install hardware | 3 | A
D | Code & test software | 4 | B
E | File take-on | 3 | B
F | Write user manuals | 10 | 
G | User training | 3 | E
H | Install & test system | 2 | C