## Slide 1: Project Management CPM An Illustrative Example
Sidra Khalid

## Slide 2: The House Construction Problem
Activity |  | Immediate Predecessors | Expected Time (days)
1 | Walls and Ceiling | 2 | 5
2 | Foundation | - | 3
3 | Roof Timbers | 1 | 2
4 | Roof Sheathing | 3 | 3
5 | Electrical Wiring | 1 | 4
6 | Roof Shingles | 4 | 8
7 | Exterior Siding | 8 | 5
8 | Windows | 1 | 2
9 | Paint | 6, 7, 10 | 2
10 | Inside Wall Board | 8, 5 | 3
Modified from Moore and Weatherford, Decision Modelling, Pearson 2001.
The Build-Rite Construction Company has identified ten activities that take place in building a house. They are

## Slide 3: Critical Path Method (CPM)
Step 1: Forward pass
Step 2: Backward pass
Step 3: Calculating
Identify the critical path(s).
interpret the meaning of slacks and critical activities.

## Slide 4: Notations
2
1
3
5
8
7
9
END
Start
0
3
5
2
4
2
8
3
0
4
10
6
3
5
2
ES | EF
LS | LF
ES: Earliest Start LS: Latest Start TS: Total Slack
EF: Earliest Finish LF: Latest Finish FS: Free Slack

## Slide 5: Step 1: Forward Pass
2
1
3
5
8
7
9
Notations
ES: Earliest Start LS: Latest Start TS: Total Slack
EF: Earliest Finish LF: Latest Finish FS: Free Slack
3
5
2
4
2
8
3
4
10
6
3
5
2
1 | 3
4 | 8
9 | 10
11 | 13
14 | 21
22 | 23
9 | 12
13 | 15
9 | 10
11 | 15
ES | EF
LS | LF

## Slide 6: Step 2: Backward Pass
2
1
3
5
8
7
9
Notations
ES: Earliest Start LS: Latest Start TS: Total Slack
EF: Earliest Finish LF: Latest Finish FS: Free Slack
3
5
2
4
2
8
3
4
10
6
3
5
2
0 | 3
3 | 8
8 | 10
10 | 13
13 | 21
21 | 23
8 | 12
12 | 15
8 | 10
10 | 15
1 | 3
1 | 3
4 | 8
4 | 8
9 | 10
9 | 10
11 | 13
11 | 13
14 | 21
14 | 21
22 | 23
22 | 23
9 | 12
15 | 18
13 | 15
19 | 21
9 | 10
15 | 16
11 | 15
17 | 21
ES | EF
LS | LF

## Slide 7: Step 3: Calculating Slacks
2
1
3
5
8
7
9
Notations
ES: Earliest Start LS: Latest Start TS: Total Slack
EF: Earliest Finish LF: Latest Finish FS: Free Slack
3
5
2
4
2
8
3
4
10
6
3
5
2
0 | 3
3 | 8
8 | 10
10 | 13
13 | 21
21 | 23
8 | 12
12 | 15
8 | 10
10 | 15
1 | 3
1 | 3
4 | 8
4 | 8
9 | 10
9 | 10
11 | 13
11 | 13
14 | 21
14 | 21
22 | 23
22 | 23
9 | 12
15 | 18
13 | 15
19 | 21
9 | 10
15 | 16
11 | 15
17 | 21
TS = 0
FS = 0
TS = 0
FS = 0
TS = 0
FS = 0
TS = 0
FS = 0
TS = 0
FS = 0
TS = 0
FS = 0
TS = 6
FS = 0
TS = 6
FS = 6
TS = 6
FS = 0
TS = 6
FS = 6
The slacks are equal to zero for all the critical activities.
ES | EF
LS | LF